## Task List
CB Zone X Task List
# | TASK | STATUS | PRIORITY | DUE DATE | Module | ASSIGNEE | NOTES | STATUS WORKING | PRIORITY KEY | Update on Progress
1 | Enrollment of user | COMPLETE | HIGH |  | PMS | AMR | Registration of users and connection of Biometrics ID (BioID + Emp ID) | COMPLETE | HIGH | PMS
2 | Updating of users | COMPLETE | MEDIUM |  | PMS | AMR |  | OVERDUE | MEDIUM | SS
3 | Uploading of users via excel | NOT STARTED | LOW |  | PMS | AMR | To be used for migration | IN PROGRESS | LOW | MW
4 | Report generation | NOT STARTED |  |  | PMS | AMR | Allow users to extract data to excel | NOT STARTED |  | AC
5 | Employee movement process | NOT STARTED |  |  | PMS | AMR | Enable employee movement thru lateral transfer to other department, promotions, onboarding & offboarding |  |  | MD
6 | Leave credit management | NOT STARTED |  |  | TK | AMR | Enable automatic leave crediting & manual crediting |  |  | TK
7 | Middleware for biometrics shakehand | COMPLETE |  |  | MW | AMR |  |  |  | APL
8 | Creation of Out of Business main page | COMPLETE |  |  | SS | AMR |  |  |  | RT
9 | Creation of OB form | COMPLETE |  |  | SS | AMR
10 | Creation of OB pending list | COMPLETE |  |  | SS | AMR | This is the list where all OB will be displayed upon creation Employee view - Allowed to cancel and update OB Approver view - Allowed to approve OB
11 | Creation of OB approved list | COMPLETE |  |  | SS | AMR | This is the list where all approved OB will be displayed Approver view - Allowed to cancel approval Employee view - Not allowed to cancel approval
12 | Creation of OB disapproved list | COMPLETE |  |  | SS | AMR | List of disapproved OB All disapproved OB will be treated as PENDING status again
13 |  | NOT STARTED |  |  |  | JNL
14 | Backend process for OB | NOT STARTED |  |  | SS | AMR
15 |  | NOT STARTED |  |  |  | JNL
16 | Creation of OT form | COMPLETE |  |  | SS | AMR
17 | Creation of OT pending list | COMPLETE |  |  | SS | AMR
18 | Creation of OT approved list | COMPLETE |  |  | SS | AMR
19 | Creation of OT disapproved list | COMPLETE |  |  | SS | AMR
20 | Add approval function for OT | COMPLETE |  |  | SS | AMR
21 | Backend process for OT | NOT STARTED |  |  | SS | AMR
22 |  | NOT STARTED |  |  |  | JNL
23 | Creation of LEAVE form | COMPLETE |  |  | SS | AMR
24 | Creation of LEAVE pending list | COMPLETE |  |  | SS | AMR
25 | Creation of LEAVE approved list | COMPLETE |  |  | SS | AMR
26 | Creation of LEAVE disapproved list | COMPLETE |  |  | SS | AMR
27 | Add approval function for LEAVE | COMPLETE |  |  | SS | AMR
28 | Backend process for LEAVE | IN PROGRESS |  |  | SS | AMR
29 |  | NOT STARTED |  |  |  | JNL
30 |  | NOT STARTED |  |  |  | JNL
31 |  | NOT STARTED |  |  |  | JNL
32 |  | NOT STARTED |  |  |  | JNL
33 |  | NOT STARTED |  |  |  | JNL
34 |  | NOT STARTED |  |  |  | JNL
35 | Self-service clock in clock out via web | NOT STARTED |  |  | SS | MAV
36 | Clock in clock out resolving | NOT STARTED |  |  | SS | MAV
| Clock in clock out approval | NOT STARTED |  |  | SS
37 |  | NOT STARTED |  |  |  | JNL
38 | Extraction of Timekeeping report to excel | NOT STARTED |  |  | RT | AMR
|  | NOT STARTED |  |  |  | JNL