## Task List
CB Zone X Task List | [10 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday
# | TASK | STATUS | PRIORITY | DUE DATE | Module | ASSIGNEE | NOTES | STATUS WORKING | PRIORITY KEY | Update on Progress | February 3, 2025 | February 4, 2025 | February 5, 2025 | February 6, 2025 | February 7, 2025 | February 8, 2025 | February 10, 2025 | February 11, 2025 | February 12, 2025 | February 13, 2025 | February 14, 2025
1 | Enrollment of user | COMPLETE | HIGH |  | PMS | AMR | Registration of users and connection of Biometrics ID (BioID + Emp ID) | COMPLETE | HIGH | PMS | Employee Management
2 | Updating of users | COMPLETE | MEDIUM |  | PMS | AMR |  | OVERDUE | MEDIUM | SS | Self-Service
3 | Uploading of users via excel | NOT STARTED | LOW |  | PMS | AMR | To be used for migration | IN PROGRESS | LOW | MW | Middleware
4 | Report generation | NOT STARTED |  |  | PMS | AMR | Allow users to extract data to excel | NOT STARTED |  | AC | Access Control
5 | Employee movement process | NOT STARTED |  |  | PMS | AMR | Enable employee movement thru lateral transfer to other department, promotions, onboarding & offboarding |  |  | MD | Master Data
6 | Leave credit management | NOT STARTED |  |  | TK | AMR | Enable automatic leave crediting & manual crediting |  |  | TK | Timekeeping
7 | Middleware for biometrics shakehand | COMPLETE |  |  | MW | AMR |  |  |  | APL | Approval
8 | Creation of Out of Business main page | COMPLETE |  |  | SS | AMR |  |  |  | RT | Report
9 | Creation of OB form | COMPLETE |  |  | SS | AMR
10 | Creation of OB pending list | COMPLETE |  |  | SS | AMR | This is the list where all OB will be displayed upon creation Employee view - Allowed to cancel and update OB Approver view - Allowed to approve OB
11 | Creation of OB approved list | COMPLETE |  |  | SS | AMR | This is the list where all approved OB will be displayed Approver view - Allowed to cancel approval Employee view - Not allowed to cancel approval
12 | Creation of OB disapproved list | COMPLETE |  |  | SS | AMR | List of disapproved OB All disapproved OB will be treated as PENDING status again
13 | Add approval function for OB | COMPLETE |  | CHECKED | SS | KPM | Allow approver to approve & disapprove OB | POLISHING | FUNCTIONS |  | Focused | Focused | Focused | Focused | Focused | Focused
14 | Backend process for OB | NOT STARTED |  |  | SS | AMR |  |  | FUNCTIONS
15 | Polish design of OB function | COMPLETE |  | CHECKED | SS | KPM | Beautification for forms and table | POLISHING | FUNCTIONS
16 | Creation of OT form | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
17 | Creation of OT pending list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
18 | Creation of OT approved list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
19 | Creation of OT disapproved list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
20 | Add approval function for OT | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
21 | Backend process for OT | NOT STARTED |  |  | SS | AMR |  |  | FUNCTIONS
22 | Polish design of OT function | COMPLETE |  | CHECKED | SS | KPM | Beautification for forms and table | POLISHING | FUNCTIONS
23 | Creation of LEAVE form | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
24 | Creation of LEAVE pending list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
25 | Creation of LEAVE approved list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
26 | Creation of LEAVE disapproved list | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
27 | Add approval function for LEAVE | COMPLETE |  |  | SS | AMR |  |  | FUNCTIONS
28 | Backend process for LEAVE | IN PROGRESS |  |  | SS | AMR |  |  | FUNCTIONS
29 | Polish design of LEAVE function | COMPLETE |  | CHECKED | SS | KPM |  | POLISHING | FUNCTIONS
30 | Change schedule filing | COMPLETE |  | FOR CHECKING | SS | KPM |  |  | FUNCTIONS
31 | HR Admin - Create Leave, preapproved | COMPLETE |  | CHECKED | TK | KPM | Reuse the codes from self-service modules just add selection of employee | POLISHING | FUNCTIONS
32 | HR Admin - Create OB, preapproved | COMPLETE |  | CHECKED | TK | KPM | Reuse the codes from self-service modules just add selection of employee | POLISHING | FUNCTIONS |  | Focused | Focused | Focused | Focused | Focused | Focused
33 | HR Admin - Create OT, preapproved | COMPLETE |  | CHECKED | TK | KPM | Reuse the codes from self-service modules just add selection of employee | POLISHING | FUNCTIONS
34 | HR Admin - Create change schedule | COMPLETE |  | CHECKED | TK | KPM |  |  | FUNCTIONS
35 | Self-service clock in clock out via web | NOT STARTED |  |  | SS | MAV |  |  | FUNCTIONS
36 | Clock in clock out resolving | NOT STARTED |  |  | SS | MAV |  |  | FUNCTIONS
| Clock in clock out approval | NOT STARTED |  |  | SS |  |  |  | FUNCTIONS
37 | Master Data Holiday Maintenance CRUD | COMPLETE |  | FOR CHECKING | MD | KPM |  | POLISHING | FUNCTIONS | [7 empty] | Focused | Focused | Focused | Focused | Focused
38 | Extraction of Timekeeping report to excel | NOT STARTED |  |  | RT | AMR |  |  | FUNCTIONS | [7 empty] | Focused | Focused | Focused | Focused | Focused
| [Settings]Cutoff window - Make function to update status (Open,Close) - Ken | COMPLETE |  | FOR CHECKING | SS | KPM |  | POLISHING | FUNCTIONS | [7 empty] | Focused | Focused | Focused | Focused | Focused