## Simple Gantt Chart - EX
Project Gantt
PROJECT TITLE | HRIS - CB Zone X
PROJECT MANAGER | Austine Redondo
COMPANY NAME | The Laguna Creamery Inc. / Bukidnon Milk Company
DATE | Novemeber 15, 2024
[7 empty] | 2024-11-01 | [19 empty] | 2024-12-01 | [24 empty] | 2025-01-01 | [19 empty] | 2025-02-01 | [19 empty] | 2025-03-01
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 24 | 26 | 27 | 28 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 24 | 25 | 26 | 27 | 28
1 | Project Conception and Initiation
1.1 | Project Charter | AMR | 2024-11-11 | 2024-11-12 | 1 | 100%
1.1.1 | Project Charter Revisions | AMR | 2024-11-13 | 2024-11-14 | 1 | 100%
1.2 | Research | AMR |  |  |  | 0%
1.3 | Projections | AMR |  |  |  | 0%
1.4 | Stakeholders | AMR |  |  |  | 0%
1.5 | Guidelines | AMR | 2025-02-10 | 2025-02-20 | 10 | 60%
1.6 | Project Initiation | AMR | 2025-01-07 | 2025-01-07 | 1 | 100%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | AMR | 2023-03-24 | 2023-03-28 | 4 | 100%
2.2 | Budget | AMR | 2023-03-29 | 2023-04-02 | 4 | 100%
2.3 | Communication Plan | AMR | 2023-03-29 | 2023-04-02 | 4 | 100%
2.4 | Risk Management | AMR | N/A | N/A | N/A | 100%
3 | Project Launch and Execution
3.2 | Deliverables | TEAM | 2025-01-09 | 2025-02-14 | 55 | 50%
3.2.1 | Employee Management | AMR | 2025-01-09 | 2025-01-17 | 7 | 90%
3.4 | Self-service | MAV/AMR | 2025-01-09 | 2025-01-17 | 7 | 60%
3.6 | Self-Service process | MAV/AMR | 2025-01-09 | 2025-01-24 | 12 | 30%
3.2.2 | Middleware of Biometrics | AMR | 2024-12-02 | 2024-12-23 | 16 | 100%
3.8 | User Management | KPM | 2025-01-09 | 2025-01-15 | 5 | 70%
4 | Role Management | MAV | 2025-01-20 | 2025-01-24 | 5 | 70%
3.2.3 | Master Data Maintenance | MAV/KPM | 2025-01-27 | 2025-01-31 | 5 | 50%
4.2 | Backend Process | AMR | 2025-01-09 | 2025-01-31 | 17 | 60%
3.3 | Demo Setup Preparation | TEAM | 2025-02-04 | 2025-02-07 | 4 | 0%
| Data Migration | TEAM | 2025-02-04 | 2025-02-07 | 4 | 0%
3.3 | Project Updates | AMR |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | AMR |  |  |  | 0%
4.2 | Quality Deliverables | AMR |  |  |  | 0%
4.3 | Effort and Cost Tracking | AMR |  |  |  | 0%
4.4 | Project Performance | AMR |  |  |  | 0%

## Simple Gantt Chart - BLANK
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%